## Budget Breakdown
Peak Gen NESO LT29 Stability Studies (Tiered Quotation)
Budget Range: € 40,000.00 - € 110,000.00
Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
Line Item 1: Study Setup (One-Time)
Kick-off meeting and coordination | 4 | 2 | 1
Review NGET Connection Feasibility Reports | 8 | 4 | 0
Validate NESO grid data (Effectiveness Sheet V7) | 4 | 2 | 1
Assess GE RS4 PowerFactory models | 8 | 4 | 2
Develop Python automation script (PowerFactory API) | 16 | 8 | 2
Develop reporting framework (data extraction, plots, proforma population) | 12 | 6 | 1
Integrate GE RS4 models and AVR systems (one-time setup) | 12 | 6 | 2
Contingency (5%) | 4 | 2 | 1
Subtotal
Line Item 2: 2 Sites x 1 Option (2 Variants, 42 Simulations)
Build network models (2 sites) | 20 | 8 | 2
Steady-state load flow validation (2 sites) | 4 | 2 | 0
Execute simulations: Test 1 (4 steps x 2 variants) | 4 | 2 | 0
Execute simulations: Test 2 (9 steps x 2 variants) | 6 | 3 | 0
Execute simulations: Test 3 (8 steps x 2 variants) | 6 | 3 | 0
Debug and re-run failed simulations | 4 | 2 | 0
Data extraction and metric calculation (2 variants) | 12 | 6 | 1
Populate Section B proforma Q44-Q149 (2 variants) | 8 | 4 | 1
Author Feasibility Study Reports per NESO Template V3 (2 reports) | 14 | 6 | 2
Generate time-series plots (42 tests) | 6 | 2 | 0
Senior technical peer review (2 variants) | 2 | 4 | 2
Address review comments and finalise | 4 | 2 | 0
Contingency (5%) | 5 | 3 | 1
Subtotal
Line Item 3: 4 Sites x 1 Option (4 Variants, 84 Simulations)
Build network models (4 sites) | 40 | 16 | 4
Steady-state load flow validation (4 sites) | 8 | 4 | 1
Execute simulations: Test 1 (4 steps x 4 variants) | 8 | 4 | 1
Execute simulations: Test 2 (9 steps x 4 variants) | 12 | 6 | 1
Execute simulations: Test 3 (8 steps x 4 variants) | 12 | 6 | 1
Debug and re-run failed simulations | 8 | 4 | 0
Data extraction and metric calculation (4 variants) | 20 | 8 | 1
Populate Section B proforma Q44-Q149 (4 variants) | 16 | 8 | 2
Author Feasibility Study Reports per NESO Template V3 (4 reports) | 24 | 12 | 4
Generate time-series plots (84 tests) | 12 | 4 | 0
Senior technical peer review (4 variants) | 4 | 8 | 4
Address review comments and finalise | 8 | 4 | 1
Contingency (5%) | 10 | 5 | 1
Subtotal
Line Item 4: 6 Sites x 2 Options (12 Variants, 252 Simulations) -- Volume Discount Applied
Build network models (6 sites, 2 config variants each) | 56 | 24 | 4
Steady-state load flow validation (12 variants) | 16 | 6 | 1
Execute simulations: Test 1 (4 steps x 12 variants) | 16 | 8 | 1
Execute simulations: Test 2 (9 steps x 12 variants) | 24 | 12 | 1
Execute simulations: Test 3 (8 steps x 12 variants) | 24 | 12 | 1
Debug and re-run failed simulations | 16 | 8 | 0
Data extraction and metric calculation (12 variants) | 40 | 16 | 2
Populate Section B proforma Q44-Q149 (12 variants) | 36 | 16 | 3
Author Feasibility Study Reports per NESO Template V3 (12 reports) | 48 | 24 | 6
Generate time-series plots (252 tests) | 24 | 8 | 0
Senior technical peer review (12 variants) | 8 | 16 | 8
Address review comments and finalise | 16 | 8 | 2
Contingency (5%) | 18 | 9 | 2
Subtotal
TOTAL HOURS & COST
Total Hours:
CLIENT SUMMARY - Work Package Overview
Work Package | Total Hours | Cost | Notes
Item 1: Study Setup (One-Time) |  |  | Technical work and deliverables
Item 2: 2 Sites x 1 Option (2 Variants, 42 Simulations) |  |  | Technical work and deliverables
Item 3: 4 Sites x 1 Option (4 Variants, 84 Simulations) |  |  | Technical work and deliverables
Item 4: 6 Sites x 2 Options (12 Variants, 252 Simulations) -- Volume Discount Applied |  |  | Technical work and deliverables
PROJECT TOTAL