Front cover. Data on this page comes from the title page overleaf and can be edited there. Delete "Document No. …" if you do not use it.

Proposal for NESO Long-Term 2029 (LT29) Stability Services Peak Gen

Customer Reference: [Customer reference] DNV doc No: [DNV doc No.] Date of first issue: [Date of issue] Date of this revision: [Date of last revision]

Title page. 1 Displayed on front cover. 2) Displayed in footer on Page 1 onwards. Tips for easy filling in data: Place cursor in the first field. Edit. Then use Tab to go to next field (Shift-Tab to go to prev.). When you reach the last field it will stop (just before Section 8.2).

Customer Details

| Customer Name:1 | Peak Gen |
| --- | --- |
| Customer Address: | [Customer Address] |
| Customer Reference:1 | [Customer Reference] |
| Contact Person: | [Contact Person] |

DNV Company Details

| DNV Legal Entity: | DNV Netherlands B.V. |
| --- | --- |
| DNV Organisation Unit: | Energy Systems |
| DNV Address: | Utrechtseweg 310-B50, 6812 AR Arnhem, The Netherlands |
| DNV Contact person | [name contact person] |
| DNV Telephone: | +31 6 xxxx xxxx |
| DNV Org. No.: | 09006404 |

About this document

| DNV doc. No.:1,2 | [DNV doc. No.] |
| --- | --- |
| Proposal Title:1 | NESO Long-Term 2029 (LT29) Stability Services |
| Date of first issue:2 | [Date of issue] |
| Date of this revision: | [Date of last revision] |
| Validity of proposal: | 3 months from date of issue |
| Terms and Conditions: | See Section Contractual |

Confidentiality

This proposal contains information that is business sensitive to DNV. No part of the proposal or information received during the proposal process may be used, duplicated or disclosed for any other purpose. Any such use of DNV’s information is regarded as an infringement of DNV intellectual property rights.

| for DNV Netherlands B.V. |  |  |
| --- | --- | --- |
| Prepared by: |  | Approved by: |
| [Name] [Name] |  | [Name] [Name] |

Table of contents

1	Introduction	1

2	The DNV proposed solution	2

2.1	Approach	2

2.2	Deliverables	2

2.3	Alternative and/or optional work	2

3	Scope of work	3

4	Schedule	4

5	Compensation	5

5.1	General	5

5.2	Lump sums	5

5.3	Rates and Expenses	5

5.4	Budget	5

5.5	Adjustment of lump sums, rates and unit costs	5

5.6	Invoicing and Payment	5

6	Project organisation	7

6.1	Organogram	7

6.2	Key Personnel	7

6.3	Resource Pool	8

6.4	Contact Information	8

7	Contractual	9

7.1	Contract basis - Terms and Conditions	9

7.2	Assumptions, conditions and limitations	9

7.3	Mandatory health and safety terms	9

8	Acceptance	9

Short Form Agreement (SFA)

# Introduction

Peak Gen has requested DNV to provide stability study services in support of their submission to the NESO Long-Term 2029 (LT29) Stability Services tender. The project involves four sites across England and Wales, each proposing GE RS4 Rotating Stabilizers to provide grid stability services including short circuit current injection, inertia, and voltage support.

DNV will perform RMS dynamic simulations using DIgSILENT PowerFactory per NESO Technical Specification V3 and Feasibility Study Requirements V5. As the RS4 machines are Grid Forming Synchronous (GBGF-S) assets, RMS modelling is the NESO-mandated approach. DNV will complete the required Tab 4 proformas to enable Peak Gen’s tender submission, with target completion in mid-April 2026.

Sites covered: Landulph (LAND2B 400kV), Indian Queens (INDQ2Q 400kV), Aberthaw (ABER2B 400kV), and Wilton (WILT2B 400kV). The base scope covers 4 solution variants (one per site), with additional configurations available on a time and materials basis.

# The DNV proposed solution

## Approach

DNV will execute a desktop-based analytical modelling study using DIgSILENT PowerFactory. The methodology is designed to meet the accelerated tender deadline by leveraging automated batch simulations. As the GE RS4 machines are classified as Grid Forming Synchronous (GBGF-S) assets operating at 0 MW, the study will utilise RMS dynamic simulations in accordance with the NESO Feasibility Study Requirements V5.

The study will be conducted in three phases:

Modelling Phase: Construction of the site-specific network models, including the Grid Entry Point (GEP) equivalents, export cables, step-up transformers, and integration of GE-provided RS4 machine and control models.

Simulation Phase: Development of a Python-based automation script to interface with the PowerFactory API. This script will execute the required 84 simulations (21 tests per variant across 4 sites) with high-resolution data capture at 1ms intervals.

Compliance Phase: Automated extraction of performance metrics (short-circuit current at 40ms and inertia values per NESO Equation 1) to populate the NESO technical returns.

## Deliverables

The Client will receive the following deliverables:

1. Technical Feasibility Report: Engineering report per NESO template with narratives and time-series plots for all 21 tests per variant.

2. Completed Technical Proforma: Tab 4 of LT2029 Stability Technical Proforma V4 for 4 configurations.

3. Simulation Datasets: CSV/Excel files with positive sequence RMS results, 1ms resolution, per NESO format.

4. PowerFactory Models: Finalized project files (.pfd) for the 4 site configurations.

## Alternative and/or optional work

The following services are excluded from the base scope but available on request:

- EMT sensitivity analysis (PSCAD or PowerFactory) if NESO/NGET requires sub-cycle transient verification.

- Reactive power optimisation studies on transformer tap settings or impedances.

- Additional configuration variants beyond the 4 included, priced on T&M basis.

# Scope of work

The work is organised into five sequential tasks to ensure all technical requirements for the NESO LT2029 tender are met.

Task 1: Project Initiation and Data Review

Facilitate a project kick-off meeting to finalise the parameters for the four selected site configurations. Review and extract connection asset data from the NGET Feasibility Reports. Validate the NESO equivalent grid data. Assess the GE-provided PowerFactory models for RMS simulation compatibility.

Task 2: Site-Specific Network Modelling

Develop four distinct network models in PowerFactory representing the Grid Entry Points for Landulph (LAND2B 400kV), Indian Queens (INDQ2Q 400kV), Aberthaw (ABER2B 400kV), and Wilton (WILT2B 400kV). Integrate the GE RS4 synchronous machine models with excitation systems and AVR. Perform steady-state load flow initialisation.

Task 3: Automated Simulation Execution

Develop a Python script using the PowerFactory API to automate the 84 required simulations (21 tests x 4 variants). Execute Test 1 (Short-circuit, 4 steps), Test 2 (Frequency/Inertia, 9 steps), and Test 3 (Voltage angle, 8 steps) per NESO V5 requirements for zero-MW GBGF-S solutions.

Task 4: Data Extraction and Proforma Population

Extract high-resolution (1ms step) positive sequence RMS time-series data. Calculate performance metrics including minimum reactive short-circuit contribution at 40ms (kA) and effective inertia per NESO Equation 1 (MWs). Populate the NESO Technical Proforma Tab 4 (Q44-Q144) for each of the 4 variants.

Task 5: Technical Feasibility Reporting

Author the Technical Feasibility Report following the official NESO template. Generate and format all required time-series plots as evidence. Perform senior technical peer review to ensure all NESO Pass/Fail criteria are addressed.

# Schedule

The total project duration is estimated to be four to five weeks from the Notice to Proceed (NTP) and receipt of all required input data. This schedule is designed to facilitate a final tender submission by the mid-to-late April 2026 deadline.

Week 1: Project Kick-off and Data Freeze - Receipt of NESO Effectiveness Sheet, GE PowerFactory models, final site specifications.

Week 2: Network Modelling Complete - Site-specific models and steady-state initialisation for 4 variants.

Week 3: Simulations Complete - Automated execution of 84 test runs and raw data extraction.

Week 4: Draft Deliverables - Draft Technical Feasibility Report and populated NESO Proforma for Client review.

Week 5: Final Handover - Implementation of final adjustments and delivery of tender-ready documents.

Key Dependencies: This schedule is strictly dependent upon the timely provision of data by the Client and third parties. GE RS4 PowerFactory models are assumed available at project start. Any delays in receiving input data will result in a corresponding adjustment to the final delivery date.

# Compensation

## General

The project will be invoiced based on a lump sum basis, adding up to, €67,339, rates and prices provided in this proposal are quoted in [currency] and exclusive of VAT or any other similar taxes.

Prices are exclusive of any form of withholding tax, sales tax, value added tax (VAT), goods & services tax, custom, excise & stamp duties and/or any other similar taxes including any surcharges levied thereon (hereinafter: Taxes). At contract negotiations it will be determined whether any Taxes will be applicable under the mandatory laws.

If and to the extent Customer has to withhold taxes, such as withholding tax, or other governmental charges according to the mandatory laws, Customer shall withhold and deduct such amounts from payments to DNV and pay the amount to the competent tax authority.

In the event that such Taxes are applicable and payable in respect of the prices, DNV retains the right to adjust the prices in such way that the net payments to DNV are equal to the prices as represented.

## Lump sums

Specify total lump sum and/or specify activities (and CTR ID’s) and associated lump sums in tabular form, if relevant.

Remove this subsection if not relevant.

Validity of lump sums and reference to 5.4.

DNV proposes a fixed-fee arrangement for the base scope of work covering 4 solution variants:

Task 1: Project Initiation and Data Review - 40 hours - €6,559

Task 2: Site-Specific Network Modelling - 107 hours - €17,237

Task 3: Automated Simulation Execution - 89 hours - €14,139

Task 4: Data Extraction and Proforma Population - 68 hours - €10,748

Task 5: Technical Feasibility Reporting - 85 hours - €15,472

Contingency (5%) - 20 hours - €3,184

TOTAL: 409 hours - €67,339

Prices are quoted in EUR, exclusive of VAT. This quotation is valid for 60 days from the date of issue.

## Rates and Expenses

Remember to specify all applicable costs, including e.g.:

- Hourly man-hour rates, by category, for work on T&M basis, estimated total if required.

- Hourly man-hour rates, by category, for variations to work on lump sum basis.

- Hourly man-hour rates, by category, for overtime work, or work outside normal working hours, requested by customer. This is applicable also for work on lump sum basis.

- Travel cost/allowances and travel time (lump sums/at cost/at cost plus).

- Licence fees (lump sums or unit costs).

- Laboratory costs (lump sums or unit costs).

- Equipment.

- Offshore or relocation charges.

- Validity of rates and prices and reference to 5.5.

Travel and lodging expenses will be charged at actual costs and travel by car will be reimbursed at 0.35 EUR/km, excluding VAT.

## Budget

For project work on T&M basis there shall normally be a budget, budget summary or estimate. Avoid this being a compensation limit.

## Adjustment of lump sums, rates and unit costs

Specify validity of rates and prices.

Include an adjustment clause and formula as applicable

Also lump sums, or portions of lump sums, should be subject to adjustments if delayed beyond the validity date due to causes outside DNV control.

All lump sums, rates, unit costs etc. quoted above are valid till <date>.

Thereafter escalation shall apply as follows:

## Invoicing and Payment

Use one or a combination of the following alternatives. Lump sums and e.g. travel time/costs may be invoiced according to different formats.

A: If monthly reimbursable:

Invoicing will be on a monthly reimbursable basis according to hours worked in the previous period.

B: Propose a payment plan for lump sum payment projects based on progress.

Invoicing will be on a monthly basis according to estimated project progress.

C: Propose a payment plan for payment milestones linked to the lump sum payment. The below shows milestone examples. DNV shall reserve the right to convert the payment plan into alternative B in the case of project suspension or delays of e.g. 4 months duration if due to causes outside DNV control.

Invoicing will be according to the following milestones:

- 25% at signing of contract

- 15% at delivery of …

- 20% after first project year

- 20%

- 20% at project completion

Make a choice

Invoicing will be as follows: 30% advance payment, 60% to be incurred to specified deliverables (specified in detail as mentioned in chapter 2.2) and 10% upon completion.

Specify payment conditions.

Payment shall be within 30 days of the invoice date.

Specify late payment penalty interest conditions, either explicitly or by reference to the applicable contract terms and conditions if included there.

# Project organisation

## Organogram

DNV is pleased to present a team of well qualified and experienced engineers for this project.

Edit the organigram as appropriate:

Project Manager: [TBD] - Overall delivery, client liaison, schedule management.

Lead Engineer: [TBD] - Technical direction, model review, report authorship.

Power Systems Engineer: [TBD] - Network modelling, simulation execution, data extraction.

Reviewer: [TBD] - Independent QA of models and deliverables.

## Key Personnel

The tables below may be expanded to include a column Category, showing personnel categories according to either DNV definition customer’s definition, as applicable. This is relevant especially for T&M type of compensation format, but may also be applicable for variations to lump sum compensation.

This section gives a brief presentation of proposed project members.

The proposed key personnel for the project are listed in the table below.

Table 6-1   Key Personnel

| Name | Project Role | Key Qualification and Experience |
| --- | --- | --- |
| NN | Project Sponsor |  |
| NN | Project Manager |  |

The table below shows an overview of expert personnel and other resources that will be involved in the project on an as-needed basis.

Table 6-2   Project Personnel

| Name | Project Role | Key Qualification and Experience |
| --- | --- | --- |
| NN |  |  |
| NN |  |  |

The resources listed above are based on DNV’s current availability schedule. Should project personnel availability change at the time of contract award or during the project execution, DNV will inform the customer of the changes of resources. DNV will aim at finding resources with the same level of competence as the resources listed.

## Resource Pool

(Remove if not used)

The core project team will draw on resources from DNV’s large resource pool as required. This will ensure flexibility where urgent and additional work is required.

DNV would like to emphasize that we have a large pool of highly qualified engineers/consultants/inspectors available within numerous disciplines. If needed due to changes in the schedule or scope of work, or to resolve additional customer challenges, a significant number of very experienced resources can be mobilized for the project.

## Contact Information

The contact person(s) shown in the table below will be pleased to answer any queries you may have in respect of this proposal.

Table 6-3   Contact information

| Name | Title | Telephone No. | Email |
| --- | --- | --- | --- |

# Contractual

## Contract basis - Terms and Conditions

Use one of the following alternatives, delete and edit as approporiate.

A: The customer has not proposed terms and conditions. NB! Remember to check that the correct short form agreement is proposed for the services DNV are offering, see DMSG-10-7-A0 List of Corporate Standard Contracts for Different Services.

DNV has issued the present proposal based on the assumption that the “DNV - General Terms and Conditions Advisory Services Energy Systems shall form the contractual basis for this project. The Terms and Conditions are exhibited in Appendix A.

B:  Customer has provided draft contract.  NB! In this case, remember to remove Appendix A. All “must-have” items from the legal review shall be included. In general all “nice-to-have” items should also be included, unless there are significant commercial reasons for not doing so. The qualifications and comments may be presented in e.g. tabular form, however, without the categorisation offered by the legal reviewer.

We have reviewed the proposed terms and conditions and state the following qualifications and/or comments:

C:  Proposal under a valid frame agreement.  NB! In this case, remember to remove Appendix A. Any proposed deviations from the frame agreement must be stated.

We propose that the work is performed under the existing Frame Agreement No. [frame agreement number/reference]

## Assumptions, conditions and limitations

It is important to state all assumptions, conditions and limitations regarding deliverables, scope of work, schedule, prices/costs, organisation etc., in order to prevent misunderstandings, scope creep, rework etc., and provide a basis for formulation of variations. (Variations may be relevant to all aspects of the contract, not just scope of work.) Important items should be included here even if they are stated elsewhere in the document.

Some sample items:

Format of deliverables and number of copies

Specific tools, equipment, methods etc

Review cycle assumptions (number of, cycle periods)

Travel cost and travel time are/are not included

Availability of the information from the customer

Customer response times, e.g. to draft reports

Definition of normal working hours, e.g. “a total 8 hours within the timeframe 0700 – 1700 hrs”.

Inclusive/exclusive of meetings (meeting time, travel time and costs)

In addition to possible assumptions, conditions and limitation stated elsewhere, this proposal is issued on the basis of the following assumptions, conditions and limitation with respect to deliverables, scope of work, schedule and costs etc.:

- GE RS4 PowerFactory models are provided in a validated, simulation-ready state at project start.

- NESO effectiveness factors and connection data sheets are available before modelling commences.

- Client provides final site configuration decisions before Week 1 data freeze.

- One round of draft review comments is included; additional review cycles may incur additional fees.

- DNV’s services are limited to desktop simulation studies; no physical site activities are included.

- This work is subject to the executed NDA between DNV and Peak Gen dated 11 March 2026.

## Mandatory health and safety terms

### Customer responsibility

The customer, or other entity having legal responsibility on the premises where DNV personnel will work, shall inform DNV of any safety and health hazards related to the work and/or any safety measures required for the work, prior to starting the work, or if such information not is available at that time, during the performance of the work.

Whenever DNV undertakes to work on site, the customer shall provide all adequate safety measures to ensure a working environment that is safe and in accordance with all relevant legislation.

### Main Principle

The DNV employee has the right to refuse to carry out an activity, when the safety conditions, according to his/her sole judgement, are not satisfactory.

### Substance abuse screening

Customer requirements specifying participation in screening programmes shall be communicated to the DNV employee prior to commencement of work.

# Acceptance

We believe this is an appropriate proposal and we are looking forward to receiving your order. In case you have any questions please contact (proposal manager or technical consultant, with contact details like telephone and or email address)

Use one of the following alternatives, delete and edit as appropriate.

A: The SFA will be used. Then use this text below.

Please send Section I – Cover Letter of the SFA duly countersigned for acceptance to Salesdesk@dnv.com or by mail to:

DNV Netherlands B.V.

Attn. Department Support (B50)

P.O. Box 9035

6800 ET ARNHEM

The Netherlands

B: The Framework agreement will be used. Then use this text below. The SFA appendix can be removed.

Please send our proposal duly countersigned for acceptance, and/or a separate written purchase order to Salesdesk@dnv.com or by mail to:

DNV Netherlands B.V.

Attn. Department Support (B50)

P.O. Box 9035

6800 ET ARNHEM

The Netherlands

B: The Framework agreement will be used. Then use this text below. The SFA appendix can be removed.

For Acceptance

Customer name:

Name:

Job title:

Date:

Signature:

Appendix A

Short Form Agreement (SFA)

Here the appropriate DNV Short Form Agreement shall be included (Preferably the General Terms and Conditions only should be included, however, if the agreement template is protected against editing the standard text then the full agreement text is to be included.). This can be downloaded from one.dnv.com/eformsweb/Forms/?a=2&s=1024, ref DMSG-10-7 Sec.7. See Also DMSG-10-7 Contract Handling

A prepopulated Page 1 of the SFA should only be included if so agreed with the customer.

This appendix shall be deleted if DNV Short Form Agreement is not the contract basis.