## Project 1
Project 1: Angerlo – Ravenstein
Budget Range: € 10,500.00 - € 13,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 30 | 12 | 2 | 7080
Stakeholder Consultation & Data Gathering | 5 | 3 | 0 | 1292
Subtotal | 35 | 15 | 2 | 8372
2.2 Comprehensive Modeling & Analysis
Build Detailed Models (380kV TenneT DTC-DOD, 50kV TenneT BML-NM) | 22 | 18 | 4 | 7516
Model 4x 10kV Cable Parallelisms (Liander B/C, ProRail I/II) | 32 | 4 | 1 | 5627
AC Corrosion & Touch Voltage Calculations | 18 | 4 | 1 | 3597
Subtotal | 72 | 26 | 6 | 16740
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 20 | 6 | 2 | 4496
Contingency | 5 | 2 | 1 | 1334
Subtotal | 25 | 8 | 3 | 5830
TOTAL HOURS & COST | 132 | 49 | 11 | 30942
Total Hours: | 192
CLIENT SUMMARY - Work Package Overview
Work Package | Total Hours | Cost | Notes
Project Management & Stakeholder Engagement | 52 | 8372 | Project coordination, meetings, data collection
Comprehensive Modeling & Analysis | 104 | 16740 | Technical calculations, simulations, compliance checks
Final Reporting & Close-out | 36 | 5830 | Documentation, final report, presentation
PROJECT TOTAL | 192 | 30942

## Project 2
Project 2: Ravenstein – Boxtel
Budget Range: € 14,500.00 - € 18,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 30 | 6 | 2 | 5946
Stakeholder Consultation & Data Gathering | 6 | 4 | 0 | 1626
Subtotal | 36 | 10 | 2 | 7572
2.2 Comprehensive Modeling & Analysis
Build Complex Models (Multiple 380kV, 110kV, 150kV Lines) | 50 | 22 | 12 | 14180
Model 3x 10kV Cable Parallelisms (Enexis A, Liander A/B) | 10 | 5 | 1 | 2626
AC Corrosion & Touch Voltage Calculations | 8 | 5 | 2 | 2567
Subtotal | 68 | 32 | 15 | 19373
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 12 | 7 | 2 | 3525
Contingency | 7 | 3 | 2 | 2044
Subtotal | 19 | 10 | 4 | 5569
TOTAL HOURS & COST | 123 | 52 | 21 | 32514
Total Hours: | 196
CLIENT SUMMARY - Work Package Overview
Work Package | Total Hours | Cost | Notes
Project Management & Stakeholder Engagement | 48 | 7572 | Project coordination, meetings, data collection
Comprehensive Modeling & Analysis | 115 | 19373 | Technical calculations, simulations, compliance checks
Final Reporting & Close-out | 33 | 5569 | Documentation, final report, presentation
PROJECT TOTAL | 196 | 32514

## Project 3
Project 3: Zweekhorst – Ommen
Budget Range: € 7,500.00 - € 9,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 30 | 4 | 1 | 5337
Stakeholder Consultation & Data Gathering | 4 | 2 | 0 | 958
Subtotal | 34 | 6 | 1 | 6295
2.2 Comprehensive Modeling & Analysis
Build Models (150kV TenneT OS-UD, OST-BXT Cables 1+2) | 50 | 22 | 3 | 12101
Model 1x 10kV Cable Parallelism (Liander B) | 10 | 8 | 0 | 2962
AC Corrosion & Touch Voltage Calculations | 4 | 3 | 1 | 1378
Subtotal | 64 | 33 | 4 | 16441
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 18 | 5 | 1 | 3786
Contingency | 4 | 2 | 1 | 1189
Subtotal | 22 | 7 | 2 | 4975
TOTAL HOURS & COST | 120 | 46 | 7 | 27711
Total Hours: | 173
CLIENT SUMMARY - Work Package Overview
Work Package | Total Hours | Cost | Notes
Project Management & Stakeholder Engagement | 41 | 6295 | Project coordination, meetings, data collection
Comprehensive Modeling & Analysis | 101 | 16441 | Technical calculations, simulations, compliance checks
Final Reporting & Close-out | 31 | 4975 | Documentation, final report, presentation
PROJECT TOTAL | 173 | 27711