## Project 1
Project 1: Angerlo – Ravenstein
Budget Range: € 10,500.00 - € 13,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 12 | 5 | 2
Stakeholder Consultation & Data Gathering | 5 | 3 | 0
Subtotal
2.2 Comprehensive Modeling & Analysis
Build Detailed Models (380kV TenneT DTC-DOD, 50kV TenneT BML-NM) | 28 | 18 | 4
Model 4x 10kV Cable Parallelisms (Liander B/C, ProRail I/II) | 8 | 4 | 1
AC Corrosion & Touch Voltage Calculations | 6 | 4 | 1
Subtotal
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 10 | 6 | 2
Contingency | 5 | 2 | 1
Subtotal
TOTAL HOURS & COST
Total Hours:

## Project 2
Project 2: Ravenstein – Boxtel
Budget Range: € 14,500.00 - € 18,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 14 | 6 | 2
Stakeholder Consultation & Data Gathering | 6 | 4 | 0
Subtotal
2.2 Comprehensive Modeling & Analysis
Build Complex Models (Multiple 380kV, 110kV, 150kV Lines) | 38 | 22 | 6
Model 3x 10kV Cable Parallelisms (Enexis A, Liander A/B) | 10 | 5 | 1
AC Corrosion & Touch Voltage Calculations | 8 | 5 | 2
Subtotal
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 12 | 7 | 2
Contingency | 7 | 3 | 2
Subtotal
TOTAL HOURS & COST
Total Hours:

## Project 3
Project 3: Zweekhorst – Ommen
Budget Range: € 7,500.00 - € 9,500.00
DNV 2026 Rates: Professional €145/h ¦ Senior €189/h ¦ Principal €231/h
Work Package / Task | Professional Hours | Senior Hours | Principal Hours | Contract Price
Hourly Rates → | 145 | 189 | 231 | (Formulas calculate automatically)
2.1 Project Management & Stakeholder Engagement
Project Management & Meetings | 10 | 4 | 1
Stakeholder Consultation & Data Gathering | 4 | 2 | 0
Subtotal
2.2 Comprehensive Modeling & Analysis
Build Models (150kV TenneT OS-UD, OST-BXT Cables 1+2) | 18 | 12 | 3
Model 1x 10kV Cable Parallelism (Liander B) | 4 | 2 | 0
AC Corrosion & Touch Voltage Calculations | 4 | 3 | 1
Subtotal
2.3 Final Reporting & Close-out
Final Report Preparation & Presentation | 8 | 5 | 1
Contingency | 4 | 2 | 1
Subtotal
TOTAL HOURS & COST
Total Hours: