Project Kick- Simonshaven 380kV - Expansion (DP2-4): EMC

Project: Simonshaven 380kV Expansion (DP2-4)
Client: SC&M II V.O.F. | End Client: TenneT
DNV Reference: OPP-00436810-PSP 25-1757

# Project Objective

To ensure the seamless electromagnetic compatibility (EMC) integration of the DP2-4 expansion (new transformers, compensation coils, bays 4 & 5) with the existing Simonshaven station (DP1). The ultimate goal is to provide a robust, auditable verification file that ensures technical integrity and regulatory acceptance by TenneT.

# Scope of Work & Methodology

DNV will execute the project in four defined tasks:

Task 1: Baseline Assessment & Site Survey

- Activity: On-site inspection of the existing DP1 station (earthing, bonding, cable routing, equipment state)

- Note: If excavation is required for inspection, this must be arranged by SC&M.

Task 2: Review & Verification of Existing Studies

- Activity: Critical review of TenneT & NUON influence studies (Inductive interference, GPR, 100µT/0.4µT zones).

- Output: Verification against specific VS2 requirements

Task 3: EMC Management Plan Development (DP2-4)

- Activity: Impact analysis of the new design.

- Zoning: Application of TenneT’s EMC eisen-zone concept (doc. 1287698 E04) to create a site-specific zoning plan (LPZ 0/1/2).

- Mitigation: Defining measures for earthing, bonding, shielding, and cable entry (CDG/Shelters).

Task 4: Final Reporting & Verification

- Activity: Consolidation of findings and creation of the Verification Traceability Matrix.

# Key Deliverables

DNV will deliver the following four documents in Dutch (PDF):

- Rapport Schouw/nulinspectie: Survey findings and baseline.

- Rapport Controle Beïnvloedingsstudie: Verification results of existing influence studies.

- DP2-4 EMC Beheersplan: The primary guidance document (Zoning, Risk Matrix, Mitigation Measures).

- Verificatierapportage: Formal demonstration of compliance with VS1/VS2 requirements.

# Schedule & Timeline

This table tracks project milestones. Update the "Current Forecast" column as the project progresses.

| Milestone | Activity | Baseline Date (Agreed) | Current Forecast / Actual | Status | Comments / Changes |
| --- | --- | --- | --- | --- | --- |
| T0 | Project Start Date | 13-11-2025 | 13-11-2025 | DONE | PO received by DNV |
| M1 | Kick-off & Info Handover | 20-11-2025 | 04-12-2025 | DONE | Kick-off held |
| M2A | On-Site Survey @ SMH380 | 10-12-2025 | 10-12-2025 | PENDING | Access confirmed. |
| M2B | Draft Report: Nulinspectie | 15-01-2026 | 15-01-2026 | PENDING |  |
| M3 | Submission of Draft Reports | 26-02-2026 | 26-02-2026 | PENDING | Includes Management Plan & Verification Report. |
| M4 | Consolidated Feedback (SC&M/TenneT) | 12-03-2026 | 12-03-2026 | PENDING | Calculated as M3 + 2 weeks. |
| M5 | Final Delivery | 31-03-2026 | 31-03-2026 | PENDING | End of March target. |

# Minutes of Meeting & Action Log

Project: Simonshaven 380kV (DP2-4)

- First meeting - Date: (kickoff) 20 November 2025

- 2nd Meeting - Date: 04-12-2025

## Action Items (Rolling Log)

This table tracks tasks. New updates are added to the "Latest Status / Comments" column with a date stamp.

| ID | Category | Description | Owner | Due Date | Latest Status / Comments [04-12]: | Status |
| --- | --- | --- | --- | --- | --- | --- |
| A01 | Inputs | Design Documentation: Provide complete set of DP2-4 drawings, layouts, SLDs, and equipment lists. | Roland (SC&M) | TBD | [04-12]: Roland to check availability and send to DNV or provide SharePoint access. | CLOSED |
| A02 | Inputs | Existing Documentation: Provide all docs listed in Inkoopspecificatie (EMC plans, influence studies). | DNV / SC&M | - | [04-12]: Receipt of documents confirmed. | CLOSED |
| A03 | Site Access | Site Survey Arrangements: Arrange permits and access for DNV survey team. | Roland (SC&M) | ASAP | [04-12]: Site access approval granted.[04-12]: Roland to send Poortinstructie link/info to Peet. | OPEN |
| A04 | Inputs | DO (Definitief Ontwerp): Provide updated DO info to DNV. | Roland (SC&M) | TBD | [04-12]: Updated info required for DNV analysis. | OPEN |

## Decisions & Agreements

This table captures fixed agreements that do not require further action but serve as a record.

| ID | Category | Decision / Agreement | Date Agreed |
| --- | --- | --- | --- |
| D01 | Team | DNV Project Manager: Peet Schutte. Technical Lead: Pieter Pretorius. | At kickoff |
| D02 | Comm. | Meeting Rhythm: Bi-weekly meetings between DNV and CwD (SC&M). | At kickoff |
| D03 | Comm. | Main Contact Persons: Peet Schutte (DNV) and Roland de Witte (SC&M). | At kickoff |

## Risk Register (Watchlist)

This table tracks risks that need monitoring throughout the project.

| ID | Risk Description | Potential Impact | Mitigation Strategy | Status |
| --- | --- | --- | --- | --- |
| R01 | Impact of EMC mitigations on Detail Design | Mitigations proposed by DNV might require changes to the already frozen or advanced Detail Design. | Early identification of major deviations during the "Nulinspectie" and Gap Analysis. | Active |