Front cover. Data on this page comes from the title page overleaf and can be edited there. Delete "Document No. …" if you do not use it.

Proposal for Iron Mountain capacity request advisory services Iron Mountain

Customer Reference: [Customer reference] DNV doc No: [DNV doc No.] Date of first issue: [Date of issue] Date of this revision: [Date of last revision]

Title page. 1 Displayed on front cover. 2) Displayed in footer on Page 1 onwards. Tips for easy filling in data: Place cursor in the first field. Edit. Then use Tab to go to next field (Shift-Tab to go to prev.). When you reach the last field it will stop (just before Section 8.2).

Customer Details

| Customer Name:1 | Iron Mountain |
| --- | --- |
| Customer Address: | [Customer Address] |
| Customer Reference:1 | [Customer Reference] |
| Contact Person: | [Contact Person] |

DNV Company Details

| DNV Legal Entity: | DNV Netherlands B.V. |
| --- | --- |
| DNV Organisation Unit: | Energy Systems |
| DNV Address: | Utrechtseweg 310-B50, 6812 AR Arnhem, The Netherlands |
| DNV Contact person | [name contact person] |
| DNV Telephone: | +31 6 xxxx xxxx |
| DNV Org. No.: | 09006404 |

About this document

| DNV doc. No.:1,2 | [DNV doc. No.] |
| --- | --- |
| Proposal Title:1 | Iron Mountain capacity request advisory services |
| Date of first issue:2 | [Date of issue] |
| Date of this revision: | [Date of last revision] |
| Validity of proposal: | 3 months from date of issue |
| Terms and Conditions: | See Section Contractual |

Confidentiality

This proposal contains information that is business sensitive to DNV. No part of the proposal or information received during the proposal process may be used, duplicated or disclosed for any other purpose. Any such use of DNV’s information is regarded as an infringement of DNV intellectual property rights.

| for DNV Netherlands B.V. |  |  |
| --- | --- | --- |
| Prepared by: |  | Approved by: |
| [Name] [Name] |  | [Name] [Name] |

Table of contents

1	Introduction	1

2	The DNV proposed solution	2

2.1	Approach	2

2.2	Deliverables	2

3	Scope of work	3

3.1	Phase 1 – Iron Mountain case and objectives	3

3.2	Phase 2 – TenneT process and engagement	3

3.3	Phase 3 – Technical options and roadmap (conditional)	3

4	Schedule	4

5	Iron Mountain resource requirements	4

5.1	Phase 1 (weeks 1–2)	4

5.2	Phase 2 (weeks 2–4)	4

5.3	Phase 3 (weeks 4–6, if applicable)	4

6	Compensation	5

6.1	General	5

6.2	Rates and Expenses	5

6.3	Adjustment of lump sums, rates and unit costs	5

6.4	Invoicing and Payment	5

7	Project organisation	6

7.1	Organogram	6

7.2	Key Personnel	6

7.3	Contact Information	7

8	Contractual	9

8.1	Contract basis - Terms and Conditions	9

8.2	Assumptions, conditions and limitations	9

8.3	Mandatory health and safety terms	10

9	Acceptance	10

Short Form Agreement (SFA)

# Introduction

Iron Mountain is seeking to upgrade its data center connection capacity from the current 30 MVA connection with Liander (medium voltage) to a 70 MVA connection with TenneT (high voltage) at the same location in Haarlem. Due to regional grid congestion, standard capacity requests face significant delays and potential rejection.

DNV proposes a technical-first approach to position Iron Mountain as an interactive grid partner rather than a passive consumer. By identifying concrete technical solutions to mitigate grid congestion—such as Battery Energy Storage Systems (BESS), demand flexibility, and grid support technologies—we will prepare Iron Mountain for substantive discussions with TenneT that focus on mutual benefit rather than one-sided capacity requests.

This proposal outlines a three-phase, gated approach. First, we clarify Iron Mountain's objectives and connection requirements. Second, together with Iron Mountain, we explore with TenneT how their current process deals with this type of request and whether there is room for a more tailored, "interactive consumer" approach. Only if there appears to be such room do we proceed to a third phase in which we further develop technical options to support the case. The work is offered on a time-and-materials basis so that the level of effort in later phases can be adjusted to what is practically possible.

# The DNV proposed solution

## Approach

Iron Mountain operates a critical data center facility in Haarlem. The site currently has a 30 MVA connection via Liander on the medium-voltage network and aims to move to a 70 MVA connection via TenneT. This request is made in a context of grid congestion in Noord-Holland, where standard capacity requests face significant delays and, in some cases, rejection. Without a differentiated technical proposal, Iron Mountain risks remaining on a waiting list for an extended period.

This project has both an immediate and a strategic objective. In the short term, the aim is to enable an increase in connection capacity from 30 MVA to 70 MVA in a way that is compatible with local grid constraints. In parallel, Iron Mountain wishes to build a better understanding of how the regional grid operates and to explore how the site can act as an interactive participant in the energy system rather than a purely passive consumer.

The focus of this project is a advise on a technical solution framework. We will analyse local grid constraints at the relevant connection points, identify technical options to mitigate congestion (for example, storage, demand flexibility and other grid support services), and prepare a set of concrete alternatives that can be discussed with TenneT. The intent is to position Iron Mountain as a party that can contribute to resolving local constraints while meeting its own capacity needs.

## Deliverables

The main deliverables foreseen in this assignment are:

- Phase 1 note describing Iron Mountain’s current connection, requested upgrade and objectives, including an initial view on acceptable and non-acceptable flexibility;

- Phase 2 process description summarising how TenneT handles this type of request in practice for the relevant connection point, what this implies for Iron Mountain, and an assessment of the apparent room for tailored solutions; and

- if justified, a short Phase 3 options note and roadmap outlining two to three technical concepts and how they could be used in future discussions with TenneT.

All deliverables will be provided in English.

# Scope of work

## Phase 1 – Iron Mountain case and objectives

Objective: obtain a clear and shared understanding of Iron Mountain’s current position, connection requirements and underlying objectives.

In this phase we review the existing 30 MVA connection, the desired 70 MVA connection at TenneT level and the reasons behind this request (capacity needs, timing, security of supply, commercial drivers). We also discuss what degree of operational flexibility Iron Mountain may be willing to consider, for example with respect to peak demand, temporary curtailment or the use of on-site resources. The review includes available load and consumption data, basic connection documentation and the main elements of past correspondence with Liander and TenneT.

The outcome of Phase 1 is a concise description of Iron Mountain’s case: what is being requested, why it is needed, what flexibility is and is not acceptable, and which constraints are non-negotiable from Iron Mountain’s perspective.

## Phase 2 – TenneT process and engagement

Objective: jointly explore with TenneT how this type of request is handled in their current process and whether there is meaningful room for tailored solutions.

In this phase Iron Mountain invites DNV to participate as technical advisor in one or more exploratory discussions with TenneT. Together we aim to clarify how queueing and capacity allocation are organised for this connection point, which steps are fixed and where, if anywhere, there is scope to take into account an "interactive consumer" approach or supporting measures on the customer side. A key question is whether and how additional flexibility or grid support from Iron Mountain could influence the handling of the request.

Based on these discussions we document the process as it applies to Iron Mountain, including the practical implications for timelines and decision points. We also provide a brief assessment of whether there appears to be sufficient room to justify further work on detailed technical options at this stage.

## Phase 3 – Technical options and roadmap (conditional)

Objective: if Phase 2 indicates that there is meaningful room for tailored solutions, develop a limited number of technical options and a corresponding roadmap that can support Iron Mountain’s case.

If the outcome of Phase 2 is positive, we proceed to outline two to three technical concepts that could help address local constraints or provide additional flexibility. These may include, for example, storage, demand response, reactive power support or other forms of grid support. For each concept we describe the main technical characteristics, the indicative order of magnitude of investment and operating impacts, and the way it could be brought into the dialogue with TenneT.

The results of Phase 3 are summarised in a short options note and an updated roadmap. If Phase 2 shows that the current TenneT process offers little or no room for such solutions at this time, Phase 3 can either be scaled back to a brief documentation of possible future directions or not carried out.

# Schedule

The work is intended to start with a kick-off meeting on 5 January 2026 at 15:00. The indicative timing below assumes that data and stakeholders are available as planned; actual dates can be adjusted in consultation with Iron Mountain and TenneT.

- Weeks 1–2: Phase 1 – review of Iron Mountain’s situation and objectives; preparation and agreement of the Phase 1 note.

- Weeks 2–4: Phase 2 – preparation and execution of one or more exploratory meetings with TenneT; preparation of the process description and assessment of room for tailored solutions.

- Weeks 4–6 (conditional): Phase 3 – development of technical options and roadmap, if Phase 2 indicates that this is justified and useful at this stage.

Short progress calls can be scheduled as needed, with at least one interim discussion at the end of Phase 1 and at the end of Phase 2.

# Iron Mountain resource requirements

To ensure efficient execution within the NTE budget, DNV will require access to the following Iron Mountain resources during the project:

## Phase 1 (weeks 1–2)

- Project sponsor or senior management: 2–3 hours total (kick-off meeting, final Phase 1 review).

- Operations / facility management: 3–4 hours total (current load profile explanation, operational flexibility discussion).

- Engineering / technical lead: 3–4 hours total (connection documentation review, technical constraints discussion).

- Commercial / legal (optional): 1 hour (review of past TenneT/Liander correspondence, if needed).

## Phase 2 (weeks 2–4)

- Project sponsor or senior management: 3–4 hours total (TenneT meeting attendance, Phase 2 decision gate discussion).

- Engineering / technical lead: 4–5 hours total (TenneT meeting preparation and attendance, technical clarifications).

- Legal / contracts (optional): 1–2 hours (review of TenneT process implications, if needed).

## Phase 3 (weeks 4–6, if applicable)

- Engineering / technical lead: 3–4 hours total (review of technical options, roadmap validation).

- Operations / facility management: 2–3 hours total (operational impact assessment of proposed options).

In addition to these scheduled interactions, DNV may require ad-hoc email or brief phone clarifications (estimated at 1–2 hours per week across all roles). Timely availability of key personnel and data will be critical to staying within the indicative timeline and NTE budget.

# Compensation

## General

The work described in this proposal will be carried out on a time-and-materials basis with a not-to-exceed (NTE) cap of €35,000 (excl. VAT). Iron Mountain will be invoiced for the actual hours worked and agreed expenses, using DNV's standard hourly rates for the staff involved, up to the NTE limit.

For planning purposes, we estimate the following order of magnitude of effort:

- Phase 1: approximately 3–5 consultant days for review, discussions and documentation;

- Phase 2: approximately 4–6 consultant days for preparation, participation in meetings with TenneT and documentation of the process; and

- Phase 3 (if carried out): approximately 4–6 consultant days for developing technical options and preparing the roadmap.

Prices are exclusive of any form of withholding tax, sales tax, value added tax (VAT), goods & services tax, custom, excise & stamp duties and/or any other similar taxes including any surcharges levied thereon (hereinafter: Taxes). At contract negotiations it will be determined whether any Taxes will be applicable under the mandatory laws.

If and to the extent Customer has to withhold taxes, such as withholding tax, or other governmental charges according to the mandatory laws, Customer shall withhold and deduct such amounts from payments to DNV and pay the amount to the competent tax authority.

In the event that such Taxes are applicable and payable in respect of the prices, DNV retains the right to adjust the prices in such way that the net payments to DNV are equal to the prices as represented.

## Rates and Expenses

The following rates apply for this assignment (all amounts excl. VAT):

- project manager / Consultant: €179 per hour;

- Senior grid integration engineer : €222 per hour;

- Technical specialist : €179 per hour: €265 per hour;

Travel and lodging expenses will be charged at actual costs and travel by car will be reimbursed at 0.35 EUR/km, excluding VAT.

## Adjustment of lump sums, rates and unit costs

All lump sums, rates, unit costs etc. quoted above are valid 3 months from the publication of this version of the proposal.

## Invoicing and Payment

Invoicing will be on a monthly reimbursable basis according to hours worked in the previous period.

Invoicing will be according to the following milestones:

Payment shall be within 30 days of the invoice date.

# Project organisation

## Organogram

DNV is pleased to present a team of well qualified and experienced engineers for this project.

## Key Personnel

DNV works on grid integration and capacity issues for network operators, large consumers and data centres in the Netherlands and other European countries. The project team proposed for this assignment has experience with:

- connection studies at transmission and distribution level;

- projects involving TenneT and regional DSOs; and

- technical option assessments for flexibility and storage solutions.

This experience is intended to support Iron Mountain in preparing a well-founded technical case for the requested capacity increase.

This section gives a brief presentation of proposed project members.

DNV has assembled a specialized team with deep expertise in grid integration, data center energy systems, and TenneT engagement.

ADD SHORT BIOS BELOW

**xx– Project Manager & Lead Consultant**

- Role: Primary point of contact, overall project delivery

- Expertise: Grid connection strategies, TSO engagement, energy transition

- Experience: xx+ years in Dutch electricity sector, extensive TenneT collaboration

- Responsibilities: Project coordination, client liaison, TenneT engagement strategy

**xx – Senior Grid Integration Engineer**

- Role: Technical lead for grid analysis and solution design

- Expertise: High-voltage grid modeling, BESS integration, power system stability

- Experience: xx+ years in transmission network planning and grid code compliance

- Responsibilities: Grid constraint analysis, technical solution development, TenneT documentation

**Technical Specialist – Energy Storage & Flexibility**

- Role: BESS and demand response solution design

- Expertise: Battery energy storage systems, frequency regulation, capacity markets

- Experience: 8+ years in energy storage projects and grid services

- Responsibilities: BESS sizing and configuration, financial modeling, grid services assessment

The proposed key personnel for the project are listed in the table below.

Table 6-1   Key Personnel

| Name | Project Role | Key Qualification and Experience |
| --- | --- | --- |
| NN | Project Sponsor |  |
| NN | Project Manager |  |

The table below shows an overview of expert personnel and other resources that will be involved in the project on an as-needed basis.

Table 6-2   Project Personnel

| Name | Project Role | Key Qualification and Experience |
| --- | --- | --- |
| NN |  |  |
| NN |  |  |

The resources listed above are based on DNV’s current availability schedule. Should project personnel availability change at the time of contract award or during the project execution, DNV will inform the customer of the changes of resources. DNV will aim at finding resources with the same level of competence as the resources listed.

## Contact Information

The contact person(s) shown in the table below will be pleased to answer any queries you may have in respect of this proposal.

Table 6-3   Contact information

| Name | Title | Telephone No. | Email |
| --- | --- | --- | --- |

# Contractual

## Contract basis - Terms and Conditions

DNV has issued the present proposal based on the assumption that the “DNV - General Terms and Conditions Advisory Services Energy Systems shall form the contractual basis for this project. The Terms and Conditions are exhibited in Appendix A.

## Assumptions, conditions and limitations

As outlined in the scope, Phase 3 is explicitly conditional on the outcome of Phase 2. If the Phase 2 assessment concludes that there is insufficient room within TenneT's current process to pursue tailored solutions, Iron Mountain may elect to close the assignment at that point.

In that scenario, Iron Mountain will only be invoiced for the hours and expenses incurred during Phases 1 and 2. No further work will be carried out and no additional fees will be charged beyond what has been documented up to the Phase 2 conclusion. This serves as a formal financial exit clause.

This proposal assumes:

- Iron Mountain has legal right to request the connection upgrade

- Basic site electrical data and load profiles are available

- No detailed physical site surveys or electrical testing are required

- TenneT will respond to connection request within reasonable timeframe (note: TenneT response times are outside DNV's control)

- No major regulatory changes during the 6-week project period

DNV's role is advisory only. We cannot guarantee TenneT approval of the connection upgrade, as this decision rests solely with TenneT based on grid conditions, regulatory requirements, and commercial considerations. Our value proposition is to maximize the probability of approval by presenting Iron Mountain as a technically sophisticated grid partner with concrete solutions to mutual challenges.

DNV is an independent technical advisor and is not part of the decision-making process at TenneT or Liander. Final decisions on connection capacity, timing and conditions rest solely with the system operators and the relevant authorities. Our role in this project is to help Iron Mountain prepare a transparent, technically underpinned proposal and to clarify the implications of different options.

## Mandatory health and safety terms

### Customer responsibility

The customer, or other entity having legal responsibility on the premises where DNV personnel will work, shall inform DNV of any safety and health hazards related to the work and/or any safety measures required for the work, prior to starting the work, or if such information not is available at that time, during the performance of the work.

Whenever DNV undertakes to work on site, the customer shall provide all adequate safety measures to ensure a working environment that is safe and in accordance with all relevant legislation.

### Main Principle

The DNV employee has the right to refuse to carry out an activity, when the safety conditions, according to his/her sole judgement, are not satisfactory.

### Substance abuse screening

Customer requirements specifying participation in screening programmes shall be communicated to the DNV employee prior to commencement of work.

# Acceptance

We believe this is an appropriate proposal and we are looking forward to receiving your order. In case you have any questions please contact (proposal manager or technical consultant, with contact details like telephone and or email address)

Use one of the following alternatives, delete and edit as appropriate.

A: The SFA will be used. Then use this text below.

Please send Section I – Cover Letter of the SFA duly countersigned for acceptance to Salesdesk@dnv.com or by mail to:

DNV Netherlands B.V.

Attn. Department Support (B50)

P.O. Box 9035

6800 ET ARNHEM

The Netherlands

B: The Framework agreement will be used. Then use this text below. The SFA appendix can be removed.

Please send our proposal duly countersigned for acceptance, and/or a separate written purchase order to Salesdesk@dnv.com or by mail to:

DNV Netherlands B.V.

Attn. Department Support (B50)

P.O. Box 9035

6800 ET ARNHEM

The Netherlands

B: The Framework agreement will be used. Then use this text below. The SFA appendix can be removed.

For Acceptance

Customer name:

Name:

Job title:

Date:

Signature:

Appendix A

Short Form Agreement (SFA)

Here the appropriate DNV Short Form Agreement shall be included (Preferably the General Terms and Conditions only should be included, however, if the agreement template is protected against editing the standard text then the full agreement text is to be included.). This can be downloaded from one.dnv.com/eformsweb/Forms/?a=2&s=1024, ref DMSG-10-7 Sec.7. See Also DMSG-10-7 Contract Handling

A prepopulated Page 1 of the SFA should only be included if so agreed with the customer.

This appendix shall be deleted if DNV Short Form Agreement is not the contract basis.