Project Kick- Simonshaven 380kV - Expansion (DP2-4): EMC

Project: Simonshaven 380kV Expansion (DP2-4)
Client: SC&M II V.O.F. | End Client: TenneT
DNV Reference: OPP-00436810-PSP 25-1757

# Project Objective

To ensure the seamless electromagnetic compatibility (EMC) integration of the DP2-4 expansion (new transformers, compensation coils, bays 4 & 5) with the existing Simonshaven station (DP1). The ultimate goal is to provide a robust, auditable verification file that ensures technical integrity and regulatory acceptance by TenneT.

# Scope of Work & Methodology

DNV will execute the project in four defined tasks:

Task 1: Baseline Assessment & Site Survey

- Activity: On-site inspection of the existing DP1 station (earthing, bonding, cable routing, equipment state)

- Note: If excavation is required for inspection, this must be arranged by SC&M.

Task 2: Review & Verification of Existing Studies

- Activity: Critical review of TenneT & NUON influence studies (Inductive interference, GPR, 100µT/0.4µT zones).

- Output: Verification against specific VS2 requirements

Task 3: EMC Management Plan Development (DP2-4)

- Activity: Impact analysis of the new design.

- Zoning: Application of TenneT’s EMC eisen-zone concept (doc. 1287698 E04) to create a site-specific zoning plan (LPZ 0/1/2).

- Mitigation: Defining measures for earthing, bonding, shielding, and cable entry (CDG/Shelters).

Task 4: Final Reporting & Verification

- Activity: Consolidation of findings and creation of the Verification Traceability Matrix.

# Key Deliverables

DNV will deliver the following four documents in Dutch (PDF):

- Rapport Schouw/nulinspectie: Survey findings and baseline.

- Rapport Controle Beïnvloedingsstudie: Verification results of existing influence studies.

- DP2-4 EMC Beheersplan: The primary guidance document (Zoning, Risk Matrix, Mitigation Measures).

- Verificatierapportage: Formal demonstration of compliance with VS1/VS2 requirements.

# Schedule & Timeline

Start Date (T0): 13 November 2025

Detail with dates

| Milestone | Activity | Timeline (Approx.) |
| --- | --- | --- |
| M1 | Kick-off & Information Handover | T0 + 1 Week |
| M2 | On-Site Survey @ SMH380 | T0 + 3 Weeks |
| M3 | Submission of Draft Reports | T0 + 10 Weeks |
| M4 | Consolidated Feedback from SC&M | T0 + 12 Weeks |
| M5 | Final Delivery | T0 + 14 Weeks |

# Critical Inputs

To maintain the schedule, DNV requires confirmation about documents received are the latest and complete:

- Design Documentation: Complete set of DP2-4 drawings, layouts, SLDs, and equipment lists.Confirmed

- Existing Documentation: All documents listed in the Inkoopspecificatie (e.g., previous EMC plans, influence studies).Confirmed

- Site Access: Arrangements for the site survey.

- DO – updated info required for DNV.

# Project Team & Communication

- DNV Project Manager + Technical support : Peet Schutte

- Technical Lead : Pieter Pretorius

- Communication

  - Rhythm: Bi-weekly DNV/CwD, And in agreement with Roland - proposed to ensure alignment with TenneT.

  - Peet/Roland main contact persons

# Risks

- Impact of EMC mitigations on Detail Design

- List possible risks